HMS UI — Detailed Sprint Plan

Full story cards, sprint goals, demo criteria · hms-web · U1–U7

Companion to HMS-UI-Sprint-Backlog; sources HMS-FRD-001/002, CLAUDE.md (hms-web) · July 2026

# Contents

# 0. Plan Parameters

| Parameter | Value |
| --- | --- |
| Cadence | 2-week sprints, same calendar as backend; UI sprint Un tracks backend set with half-set lag |
| Team assumption | 2–3 frontend developers + shared designer; velocity calibrated in U1 (plan ~24–30 pts/sprint at 3 devs) |
| Definition of Done | Per CLAUDE.md §3.3: design-system-only, i18n en+te, role/flag gated, 4 states built, a11y, typed API committed, tests; flow tickets update Playwright |
| Demo rule | From U3 onward, every sprint review demos BOTH flagship flows end-to-end; a broken demo blocks the sprint from closing |
| Mock rule | If a backend dep slips, build against MSW + generated types; swapping to live API must be a compile-checked change, not a rewrite |
| India rules | Telugu strings within-sprint; ₹/date formats; commission UI never renders (flag-gated); synthetic data only |

Open item carried in (flag F1). Follow-up booking is DRAFT (clinician creates draft appointment; staff/patient books slot). Confirm with client before U4 planning; UI-404 is written to DRAFT.

# Sprint U1 — Design System, Shell, First Live Screen

Sprint goal & demo: A running app with the complete MediGo component kit on /design, role-gated shell, dev login, i18n toggle, typed API pipeline, and a production-quality Patients screen against the live backend. Demo: log in as two tenants and show isolated patient lists; walk the /design page.

| UI-101 MediGo component kit + /design reference | 8 pts |
| --- | --- |

As a frontend developer, I want the full primitive set (Button, Chip, RadioPill, FieldCell, DateChips, StatusPill, Card, Modal, Drawer, Toast, Input, Select, Skeleton) built from tokens and shown on /design so that every later screen composes instead of styling

- All primitives use tokens only; grep for hex values outside tokens.css returns none

- Each primitive has keyboard + focus-visible behavior and labelled variants on /design

- StatusPill covers info/warn/success/danger/brand with correct tinted pairs

- Modal traps focus; Toast auto-dismisses ~2.5s and is announced via aria-live

- Vitest a11y smoke (axe) passes for every primitive

Traces: CLAUDE.md Part 1   Backend dep: none

| UI-102 App shell & navigation | 5 pts |
| --- | --- |

As a any user, I want a sticky header shell with logo, role-gated nav, tenant·role indicator, and logout, over the sky wash so that screens share one consistent frame

- Nav items render per role (receptionist: Patients/Billing; physician: Patients/EMR; admin: +Settings)

- Route guard redirects unauthorized roles with a friendly message

- ₹ and Indian date helpers exposed and used by all screens

- 404 and error-boundary pages styled per the error-state pattern

Traces: IAM-002 (UI mirror)   Backend dep: none

| UI-103 Auth provider hardening | 3 pts |
| --- | --- |

As a developer, I want the dev login flow productionized (tenant+role picker, 401 auto-redirect, logout clears state) behind useAuth() so that OIDC can replace internals later without touching screens

- 401 from any API call routes to login with a session-expired notice

- No token in localStorage/sessionStorage (memory only)

- useAuth() is the only auth import used by screens (lint rule enforces)

Traces: IAM-001/003 UI side   Backend dep: auth stub (exists)

| UI-104 Typed API + mock pipeline | 5 pts |
| --- | --- |

As a developer, I want generate:api producing committed schema.d.ts and an MSW setup mirroring the spec so that contract drift is a compile error and unshipped endpoints are mockable

- npm run generate:api regenerates from the backend spec; CI fails if schema is stale vs. spec artifact

- client.ts consumes generated types; temporary hand types removed for covered endpoints

- MSW handlers exist for patients endpoints; toggled via env for dev-without-backend

Traces: INT-007   Backend dep: /openapi.json (exists)

| UI-105 Patients screen production pass | 3 pts |
| --- | --- |

As a receptionist, I want search with debounce, loading skeletons, empty & error states, and ABHA badge on the list so that the first screen sets the quality bar

- 300ms debounce; results update without layout shift

- Error state offers retry; empty state offers Register action (role-gated)

- Telugu strings complete for this screen

Traces: REG-005   Backend dep: GET /patients (exists)

| UI-106 i18n foundation | 5 pts |
| --- | --- |

As a AP user, I want the app in English or Telugu via a persistent toggle, with all U1 strings keyed so that localization is structural, not retrofitted

- i18next configured with en/te namespaces; toggle in header; choice survives navigation

- Lint rule blocks string literals in JSX

- Number/date/currency formatting respects locale

Traces: POR-008   Backend dep: none

# Sprint U2 — Registration & Referral Capture

Sprint goal & demo: Front desk can fully register a patient — with duplicate check, consents, and referrer capture — and every clinical screen gains the patient header with the allergy banner slot. Demo: register a referred-in patient end-to-end, trigger the duplicate interstitial, show the referrer on the record.

| UI-201 Full registration form | 8 pts |
| --- | --- |

As a receptionist, I want a complete registration form (names, DOB, sex/gender, identifiers, contacts, address, next of kin, insurance) with per-region validation and consent capture so that patients are registered correctly the first time

- react-hook-form + zod; zod schema mirrors API constraints from generated types

- Mandatory fields driven by tenant config; identifier format errors are field-level and plain-language

- Consent checkboxes render versioned consent labels; unchecked required consent blocks save with explanation

- Success shows toast + routes to the new record; failure preserves input

Traces: REG-001/002, PLT-010   Backend dep: REG create/config APIs

| UI-202 Duplicate-match interstitial | 5 pts |
| --- | --- |

As a receptionist, I want ranked candidate matches with similarity scores before creating a possible duplicate so that the MPI stays clean

- On save with candidates, an interstitial lists matches (name, DOB, phone, score) with Open record / Not a match

- Create proceeds only after explicit Not a match; that choice is sent to the API

- Keyboard navigable; screen-reader announces the interstitial purpose

Traces: REG-003   Backend dep: MPI match API

| UI-203 Referrer capture | 5 pts |
| --- | --- |

As a receptionist, I want a searchable referrer lookup with quick-add, plus referral reason and requested service on registration/visit so that the referral flow starts with clean attribution

- Typeahead over referrer master; quick-add modal (name, type, org, phone) creates and selects

- Referral reason and requested service (e.g. CT scan) captured and shown on the record

- Referrer type displays; no commission fields anywhere (India lock)

Traces: REF-010/012, AP-4   Backend dep: referrer master API

| UI-204 Patient header component | 3 pts |
| --- | --- |

As a clinician, I want a persistent patient header (name, age/sex, ABHA badge, consent chips, allergy banner slot) reused across all clinical screens so that context is always visible and consistent

- Header is one component consumed by every patient-scoped route

- Allergy banner shows list or explicit No known allergies; absent assertion shows Assert-allergy prompt (orange)

- Banner never scrolls out (sticky under shell)

Traces: EMR-005, PLT-010   Backend dep: patient read API

| UI-205 Tenant settings (read/basic) | 5 pts |
| --- | --- |

As a tenant admin, I want a settings screen showing branding, locale defaults, and feature flags, with commission visibly locked for India so that admins see their configuration truthfully

- Flags render on/off; ref_commission renders as Locked for this region with info tooltip

- Branding preview uses tenant logo/colors within token constraints

- Edits limited to safe fields this sprint (locale display prefs); rest read-only

Traces: PLT-003/007, AP-4   Backend dep: tenant config API

# Sprint U3 — Scheduling, Prerequisites, Check-in

Sprint goal & demo: Booking with the prerequisite checklist and a check-in that enforces hard-stops. First end-to-end demo of flagship flow #1 up to check-in: register referred patient → book CT with prereqs → blocked check-in until resolved.

| UI-301 Calendar & booking | 8 pts |
| --- | --- |

As a receptionist, I want day/week calendars per practitioner with slot booking, conflict feedback, and an earliest-slot finder so that appointments are made in seconds

- Day and week views; booked/blocked/available visually distinct using tokens

- Booking modal uses FieldCell summary (service, practitioner, date, time) before confirm; MediPass on success

- Conflict/overbook errors surfaced inline with the rule that blocked them

- Earliest-slot search returns options across selected practitioners in <2s perceived

Traces: SCH-001/002/004   Backend dep: SCH endpoints

| UI-302 Prerequisite checklist on booking | 5 pts |
| --- | --- |

As a receptionist, I want service prerequisites shown at booking as a structured plain-language checklist so that patients arrive prepared

- Prereqs render from the library with hard-stop vs advisory styling (danger vs warn)

- Each item shows patient-facing text (e.g. Fast for 12 hours) with Telugu

- Checklist attaches to the appointment and is visible from the appointment card

Traces: REF-060   Backend dep: prereq library API

| UI-303 Check-in with hard-stop enforcement | 5 pts |
| --- | --- |

As a front desk, I want check-in that blocks when a hard-stop prerequisite is unmet, with the reason and resolution path so that unsafe service delivery is prevented, clearly

- Unmet hard-stop: danger panel names the item, why it blocks, and how to resolve; check-in disabled

- Advisory unmet: warn panel, check-in allowed with acknowledgment

- Resolution updates state live; audit-relevant actions call the API, never client-only

Traces: REF-061   Backend dep: check-in API

| UI-304 Walk-in queue board | 5 pts |
| --- | --- |

As a front desk, I want a live queue with status pills, wait times, and click-to-advance so that the waiting room is managed at a glance

- Statuses Arrived→In consult→Done advance via API; optimistic update with rollback on error

- Wait time per row; totals update; board refreshes on events/poll ≤10s

- Physician view filters to own room

Traces: SCH-005   Backend dep: queue API

| UI-305 Reminder preview | 3 pts |
| --- | --- |

As a tenant admin, I want a preview of reminder content per template/locale including prerequisites so that what patients receive is verifiable

- Preview renders SMS/email templates with merged appointment + prereqs, per locale

- Confirm/cancel links shown as placeholders with explanation

Traces: SCH-006, POR-009   Backend dep: notification templates

# Sprint U4 — EMR, Prescribing, Follow-up (Flagship #2)

Sprint goal & demo: Clinicians document, prescribe with safety alerts, and set the next visit with prerequisites at sign-off. Demo: full flagship flow #2 — encounter → Rx with allergy alert override → next-visit panel → DRAFT follow-up visible with prereqs.

| UI-401 Patient summary | 8 pts |
| --- | --- |

As a physician, I want a one-screen summary (problems, meds, vitals trend, recent results, encounter timeline) under the patient header so that I grasp the patient in seconds

- Loads with skeletons; perceived <3s at NFR volumes (measure with mock latency)

- Vitals trend chart (token colors, accessible descriptions); out-of-range flagged warn

- Timeline entries link to encounters; print produces a clean summary (EMR-011 base)

Traces: EMR-004/006/007/010   Backend dep: EMR read APIs

| UI-402 Encounter documentation & sign-off | 8 pts |
| --- | --- |

As a physician, I want template-driven notes with autosave, sign-off that locks content, and addenda after signing so that documentation is fast and trustworthy

- Template sections render structured fields + rich text; autosave indicator (saved · time)

- Sign-off modal states immutability; signed note shows locked badge; edit becomes Add addendum

- Diagnosis (ICD-10 search) required before sign-off when visit type demands (config)

- Unsaved-changes guard on navigation

Traces: EMR-002/003/008   Backend dep: encounter APIs

| UI-403 Prescription composer with safety alerts | 8 pts |
| --- | --- |

As a physician, I want a structured sig builder with severity-graded interaction/allergy alerts and coded-reason override so that prescribing is quick and safe

- Sig fields (drug search <1s, dose, route, frequency, duration, qty, refills); incomplete blocks sign

- Alerts render by severity (danger blocks until coded override reason; warn acknowledges)

- Override reason is a coded select + optional note; sent to API; visible on the Rx record

- Favorites list per prescriber (read) for one-click reuse

Traces: RX-002/003/007   Backend dep: RX endpoints

| UI-404 Next-visit panel at sign-off | 5 pts |
| --- | --- |

As a physician, I want to set follow-up (date or interval, reason, specialty) and attach structured prerequisites in the same sign-off action so that the return visit is planned before the patient leaves

- Panel offers interval chips (1w/2w/1m/custom date) + reason + specialty

- Prereqs picked from the library (searchable); free text only as flagged fallback

- On sign-off a DRAFT follow-up appears on the record with prereqs (flag F1)

- Medication-driven prompts (RX-009) pre-fill the panel when applicable

Traces: EMR-013/014, RX-009   Backend dep: follow-up API

| UI-405 Visit summary print/PDF | 3 pts |
| --- | --- |

As a patient-facing staff, I want a printable summary including follow-up date and plain-language prerequisites on tenant letterhead so that patients leave with clear instructions

- PDF/print includes diagnosis, Rx list, follow-up + prereqs in patient language (en/te)

- Layout verified for A4; no truncation at long med lists

Traces: EMR-011/015   Backend dep: PDF endpoint

# Sprint U5 — Orders, Results, Billing, Referral Close

Sprint goal & demo: The referred test is ordered, resulted, reviewed, billed with the Aarogyasri indicator, and the referral timeline closes the loop. Demo: flagship flow #1 complete — referral → prereq-gated CT → result review → invoice → timeline.

| UI-501 Lab/imaging ordering | 5 pts |
| --- | --- |

As a physician, I want ordering from the catalog with specimen/prep info and live order status so that orders are correct and trackable

- Catalog search (LOINC-mapped) with panels; priority routine/urgent

- Specimen & prep requirements displayed at order time (mirrors prereq language)

- Status chips follow the lifecycle ordered→collected→in-lab→resulted→reviewed

Traces: ORD-001/006   Backend dep: ORD endpoints

| UI-502 Results inbox & trends | 8 pts |
| --- | --- |

As a physician, I want a review inbox with abnormal/critical flags, acknowledgment, and cumulative trends so that no result slips through

- Inbox sorts critical→abnormal→normal; flags use warn/danger correctly

- Acknowledge per result; unacked criticals visibly escalate (per ORD-004 timing shown)

- Trend view per analyte: table + chart across time; export not required this sprint

Traces: ORD-004/005   Backend dep: results API

| UI-503 Invoice screen | 8 pts |
| --- | --- |

As a billing clerk, I want auto-captured charges with payer/patient split, reasoned edits, and the Aarogyasri/PMJAY cashless indicator so that billing is accurate and scheme-aware

- Draft lines from encounter events; add/edit/remove requires reason code (role-gated)

- Split view: payer vs patient share; totals & tax live-update

- Aarogyasri-eligible patients show scheme badge and cashless path; ineligible show why

- Finalize locks the invoice; further changes via credit-note pattern messaging

Traces: BIL-002/004, AP-2   Backend dep: BIL endpoints

| UI-504 Payments & till | 5 pts |
| --- | --- |

As a cashier, I want payment capture (cash/card), partials, receipts, and an end-of-day till summary so that collections reconcile daily

- Payment modal supports partials; balance updates; numbered receipt view/print

- Till summary by user: collected by mode, over/short display

- Refund entry visible but routes through approval messaging (BIL-008)

Traces: BIL-005/008   Backend dep: payments API

| UI-505 Referral timeline | 5 pts |
| --- | --- |

As a clinician/front desk, I want a timeline on the record: referrer → requested service → statuses → linked follow-up so that the referral loop is visibly closed

- Timeline shows origin (referrer, date, reason), service status, result availability, follow-up link

- States styled with status pills; each node links to its record

- No monetary/commission info anywhere (India lock)

Traces: REF-064, AP-4/5   Backend dep: referral timeline API

# Sprint U6 — Patient Portal, Dashboards, E2E Gate

Sprint goal & demo: Patients see their visits, prereqs, results, and pay bills on mobile; ops get the live dashboard; both flagship flows are locked in Playwright as the CI gate. Demo: the portal journey on a phone + green E2E runs.

| UI-601 Patient portal core | 8 pts |
| --- | --- |

As a patient, I want a mobile-first portal: upcoming visit with plain-language prereqs, released results, invoices with online payment so that I can manage my care from my phone

- Patient role renders portal layout (380px-first, 44px targets, bottom action bar)

- Upcoming visit card lists prereqs in plain language (en/te) with done-checkboxes (local aid only)

- Results appear per release rules; each view is an audited API read

- Invoice pay via payment connector; success shows receipt + MediPass-style confirmation

Traces: POR-002/004/005, ORD-008   Backend dep: portal + payment APIs

| UI-602 Pre-visit forms & consents | 5 pts |
| --- | --- |

As a patient, I want assigned questionnaires and consents by appointment type, completed before arrival so that clinic time isn't spent on paperwork

- Forms render from definitions; progress saved; submission attaches to the upcoming encounter

- Clinician-side flag appears on the encounter when forms are complete

- Consent signing uses the versioned consent text

Traces: POR-003, PLT-010   Backend dep: forms API

| UI-603 Ops dashboard | 5 pts |
| --- | --- |

As a clinic manager, I want today's visits, queue length/wait, no-shows, and revenue with a freshness indicator so that the day is run on data

- Tiles + simple charts (token colors); freshness ≤5 min indicator

- Site selector; role-gated; identifiable drill-downs deferred to reports

Traces: RPT-001   Backend dep: RPT APIs

| UI-604 Reports & referral analytics | 3 pts |
| --- | --- |

As a manager, I want standard report views (visits, revenue, no-shows, referral attribution) with CSV export so that decisions and referrer relationships are informed

- Filters: date range, site; CSV export; referral attribution by referrer/type/service

- Commission-related views absent for India tenants (flag-gated at route level)

Traces: RPT-002, REF-044, AP-4   Backend dep: reporting APIs

| UI-605 Playwright E2E — the UI gate | 8 pts |
| --- | --- |

As a team, I want two E2E specs walking flagship flow #1 and #2 against the compose stack, wired into CI so that the product's core promises are machine-verified on every change

- Spec 1: register referred patient → book CT with prereqs → blocked then resolved check-in → result → invoice → timeline

- Spec 2: encounter → Rx with alert override → next-visit panel → DRAFT follow-up with prereqs → visible in portal

- Runs headless in CI against docker compose; failure blocks merge

- Fixtures synthetic; specs use i18n keys not raw strings where feasible

Traces: both flows   Backend dep: full stack demoable

| UI-606 A11y + i18n sweep | 5 pts |
| --- | --- |

As a every user, I want a WCAG 2.2 AA audit pass and 100% Telugu coverage of shipped strings so that the product is usable by all AP users

- axe audit across routes: zero serious/critical; issues fixed or ticketed with owner

- te resource coverage 100% of shipped keys; pseudo-locale check for truncation

- Keyboard-only walkthrough of both flagship flows recorded as checklist

Traces: POR-008, CLAUDE.md a11y   Backend dep: —

# Sprint U7 — Release Readiness (Design-Partner Go-Live)

Sprint goal & demo: The UI is ready to put in front of a real hospital: hardened errors, performance, observability, onboarding polish, and print/browser coverage. Demo: a full design-partner walkthrough script executed without a developer touching the keyboard.

| UI-701 Error & session hardening | 5 pts |
| --- | --- |

As a user, I want graceful handling of API downtime, expired sessions, and partial failures across all screens so that real-world conditions don't strand users

- Global error boundary with retry; offline banner on fetch failures; queued toast on recovery

- Session expiry mid-form preserves input through re-auth (matches IAM-003 behavior)

- All error copy reviewed: plain language, en+te

Traces: IAM-003 UI, NFR   Backend dep: —

| UI-702 Performance pass | 5 pts |
| --- | --- |

As a user, I want fast perceived loads on modest hardware and networks so that AP clinic machines and 4G are the real baseline

- Route-level code splitting; bundle budget set and CI-checked

- Patient summary & calendar meet perceived-load targets on throttled profile (Fast 3G/low-end CPU)

- Images/fonts optimized; no layout shift on primary screens (CLS ≈ 0)

Traces: NFR performance   Backend dep: —

| UI-703 Frontend observability | 3 pts |
| --- | --- |

As a team, I want error tracking and basic usage telemetry wired with privacy guards so that we see real-world failures before users report them

- Error tracker (e.g. self-hosted Sentry) capturing release + route; PII scrubbing verified

- No patient-identifying data in events; telemetry opt-out honored per tenant

Traces: PLT privacy rules   Backend dep: ops endpoint

| UI-704 Onboarding & empty-tenant polish | 5 pts |
| --- | --- |

As a new tenant staff, I want first-run experience: seeded-tour of key screens, helpful empty states, and a getting-started checklist so that a design partner's first hour is smooth

- Empty states across modules reviewed to guide the first action

- Getting-started checklist (register first patient, set schedule, first booking) driven by real API state

- Demo script for partner walkthrough documented in repo

Traces: onboarding-as-product   Backend dep: tenant provisioning

| UI-705 Print & browser matrix | 3 pts |
| --- | --- |

As a staff, I want correct print output (summaries, receipts, MediPass) and verified support on the browser matrix so that paper and older browsers still matter in clinics

- Print stylesheets verified A4: visit summary, invoice/receipt, MediPass

- Matrix pass: evergreen Chrome/Edge/Firefox/Safari + Android WebView (portal)

- Defects fixed or consciously waived with ADR note

Traces: EMR-011, BIL-005, NFR compat   Backend dep: —

# Sprint Exit Summary

| Sprint | Exit criteria (all required) |
| --- | --- |
| U1 | /design complete & a11y-clean; shell+login+i18n live; Patients screen at quality bar; typed API + MSW working; velocity measured |
| U2 | Referred patient registrable end-to-end with duplicate check & consents; patient header with allergy banner on all clinical routes |
| U3 | Flow #1 demoable to check-in incl. hard-stop block; queue board live; reminders previewable |
| U4 | Flow #2 demoable end-to-end (encounter→Rx alert→next-visit DRAFT); summary meets perceived-load target |
| U5 | Flow #1 demoable end-to-end through invoice + timeline; Aarogyasri indicator correct for eligible/ineligible fixtures |
| U6 | Portal journey on mobile; both Playwright specs green in CI and blocking; a11y audit zero serious; te coverage 100% |
| U7 | Partner walkthrough script runs clean; perf budgets in CI; observability live with PII scrubbing verified |

Total planned: 33 stories, ~180 points across seven sprints (≈14 weeks at the assumed velocity). U1–U2 can start immediately against existing endpoints and mocks; U3+ tracks backend delivery per the alignment model. Re-estimate at each planning; this document is the baseline and lives in docs/ of hms-web — update it when scope or flags change.